## Sheet1
Issue Log
Prepared By: Jane Jung
# | Issue Description | Impact on Project | Report date | Reported by | Assigned To | Priority (Low/Medium/High) | Resolve date | Status | Solution | Comments
1 | Late team formation | Reduced amount of time for the project by a week | 2023-03-27 | Jane | Jane | High |  | Active | Will be working during weekends if necessary | entry 8: we started meetings on Saturday to catch up on proposal
2 | Scheduling issue | Everyone’s timetables during the week clash which prevents the team from having meetings | 2023-03-27 | Jane | Everyone | High | 2023-03-13 | Closed | Everyone agreed to meet during the weekend (Saturday)
3 | Communication with client | Client prefers Mandarin over English which none of us can speak | 2023-03-28 | Matthew | Matthew | Medium | 2023-03-16 | Closed | Matthew acted as the translator during the meeting, and the client agreed to give us his email if we needed further clarifications
4 | Behind schedule | Lack of information of the project delayed the start of the proposal | 2023-03-14 | Matthew | Jane | High | 2023-03-15 | Closed | Wrote out the proposal’s template, will be updating regularly with completed plans | 18/03/23: The weekend meetings put us back on track
5 | Lots of requirements | The project requires lots of different components that all require different skillsets | 2023-03-16 | Jane | Everyone | High | 2023-03-16 | Closed | Will designate tasks between members based on their skills, as we may start upskilling before submitting proposal. | 18/03/23: We separated the tasks by techical field and assigned pairs to each task, so that components could be developed evenly between team members
6 | Meeting time with mentor not spent productively | The team wasted a lot of time during the meetings trying to remember questions we wanted to ask | 2023-03-18 | Jane | Josh | Medium | 2023-03-18 | Closed | Start meeting 30 minutes before mentor meeting so we can quickly make a summary of the items we want to discuss | 21/03/23: we met 30 minutes before the mentor meeting as planned; it was decidedly more helpful to spend some time organizing what we wanted to say.
7 | Covid-Isolation | Jane became a household contact and couldn't meet in person for a week | 2023-04-02 | Jane | Team | Low | 2023-04-04 | Closed | Jane joined the meetings online, and communicated intline through discord for assigned tasks
8 | Project schedule too vague | Our project schedule presented in the proposal was pointed out for being too vague; this way we wouldn't be able to clearly establish the steps we used to complete these tasks and properly prepare to develop the components | 2023-04-04 | Tony (Moderator) | Team | High | 2023-04-11 | Closed | Will create milestones and arrange deadlines for them so that we would have an indication of our project progression | 11/4/23: updated project schedule to include milestones
9 | Jadcup source code | The team wanted access to the source code to the machines at Jadcup, as they wanted to try and make the simulation as compatible as possible with real-life scenarios but were unsure whether Daniel (client) would be willing to give access to the source code | 2023-04-21 | Josh/Myles/Yeran | Matthew | Low | 2023-05-09 | Closed | Matthew said he might bring it up with Daniel later on | 9/05/23: We decided we wouldn’t need the source code
10 | Team meetings are unreliable | The team meetings we were having during the weekend were irregular, and it felt like we weren't being productive during them either as everyone was too unmotivated early in the morning during weekends. | 2023-04-29 | Myles | Team | Medium | 2023-05-02 | Closed | Myles suggested we move the team standup meetings to after the mentor meetings on Tuesday when everyone was at least more likely to be on campus and available. The team decided to try out the meetings next week and declide which meeting worked better later. | 2/5/23: we tried the meeting on tueday, and everyone agrred that this timeslot worked better for them, and so we finalized the meeting time change.
11 | Yeran injured | Yeran got into an accident on the motorway on his way to campus | 2023-05-09 | Yeran | Yeran | Low/Medium | 2023-05-09 | Closed | He's fine, only had mild injuries. He'll stay at home for today and recover
12 | Flooding | We were supposed to have a mob session on Tuesday, but there was a flood warning that advised everyone to go home as soon as possible. The mob session is important for the team to make progress as everyone seems to work better in person, especially with the proposal presentation coming up | 2023-05-09 | Josh | Team | Medium | 2023-05-12 | Closed | We rescheduled to have the mob session on Friday same week | 12/5/23: The team had the catch up meeting online
13 | Delayed milestone | We had scheduled to complete the web application's UI prototype, but because we were busy doing the prototype, we didn't do any work towards completing the web application design. Having a prototype that displayed the functionality of our project was an important marking criteria, so so our mentor was concerned that we weren't close to finishing it. | 2023-05-16 | Matthew | Jane/Harshil | Medium/High | 2023-05-16 | Closed | We used the mob session following the meeting to start creating a draft prototype. | 19/5/23: finished UI prototype
15 | Marking criteria | Tony (moderator) pointed out that the status report we wrote and our presentation wasn't short and succinct, violating the standards set out in the assessment guidelines. However, the team and Matthew (mentor) had no choice but agree to go over the limit due to the large amount of deliverables required for marking. | 2023-05-31 | Tony | Team | Medium | 2023-05-31 | Closed | Sent Tony and email outlining the requirements and stating how realistically it is inevitable for our team to have a longer status report | 3/06/23: Tony gave us the clear (get it lol)
14 | Trello board is unorganized | There was criticism that we weren't using our Trello board efficiently- we had a lot of lists which cluttered up the page and had issues separating tasks into subtasks. This meant that the documentation to track our progress wasn't clear, which would be problematic for the team when we wanted to clarify what tasks we were up to. | 2023-05-31 | Tony | Team | Medium/High | 2023-07-22 | Closed | We had a group meeting as a team to reorganize the trello board to follow the Kanban procedure more effectively
17 | Tech stack restrictions for PLC
18 | Component relationships unclear | There was confusion regarding the component relationships, such as how the database retrieves values from the PLC, how the middlend communicates between the factory IO simulator and converts data to JSON etc. It seemed like all the members had different ideas on how the relationships worked, which caused members to develop under different assumptions for a while. | 2023-06-28 | Myles | Josh/Yeran | High | 2023-07-18 | Closed | The team had a meeting in person so that we could draw out the component diagram together and gain insight on everyone's ideas. We then debated the feasability of the relationships and commited to a final version. | 22/7/23: Josh made final component diagram
19 | Team's project planning is unstable | Due to the irregular meetings and lack of proper testing and validation of task completion, the team has arrived at a standstill where noone quite knows what we need to do | 2023-08-04 | Matthew | Team | High |  |  | Trying to redesign project methodology/update trello board/more frequent communication | new team meeting schedule and trello board (5/8/23)
20