## Sheet1
Risk Register for Jadcup Digital Factory Automation
Prepared by: |  | Yeran Edmonds & Harshil Patel |  |  |  |  | Date: | 2023-03-13
No. | Threat | Risk | Description | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
1 | Medium | Unclear Requirements | The design and necessary features of the project may be and remain unclear throughout the project | The project is as new for the client as it is for the team |  | Keep open and clear communication with the client's requirements | Client Liaison | Medium | High | Watching | 1
2 | Low-Medium | Incorrect work performed | With uncertainty of outcomes or requirements, work may be wasted in unnecessary areas | Unclear, undocumented team direction |  | Clarify work with the team, mentor and client regularly | Team Manager | Low | Medium | Unresolved
3 | Medium | Scope Creep | The work required for the project may gradually increase and overwhelm the team | Designing or discussing features that don't align with the prototype MVP |  | Check each feature aligns with the MVP | Whole Team | High | High | Unresolved
| Low-Medium | Mismanaged feature prioritization | Features incorrectly prioritized may result in delays if one system requires on another, undelivered system (AKA, the web frontend relying on the backend & db) | Poorly managed and discussed features. Improper discussion on slow-to-implement systems |  | Weekly meetings to discuss prioritization and delays | Whole Team | Medium | Low | Unresolved
5 | Low-Medium | Poor product design | The tech stack or user design may be irrelevant to the prototype's end goals | Research and discussion not properly performed between the team and client |  | Be as thorough as the team can be with tech stack research and keep discussion open with the team. | Whole Team | Low | Medium | Watching
6 | High | Poor communcation with the client | Poor communication with clients can impact on the final project as well as the team, which can lead to problems like dissatisfied clients and pressure for the team. | The client's naive language might not be English, which can lead to difficulties in understanding what the clients wants and does not want as well as the team not able to give an answer or question related to the project. Additionally, client communication is minimal and client meetings are very infrequent, lacking feedback or discussion about the project. | If the client gets back to us with a slew of changes, we know this risk has become an issue. | Send demos and reviews to the client for them to get back to us. Any feedback from the client can be baked into our change management through iteration or design planning. In the meantime, get assistance from our mentor regarding requirements and feedback as part of our change management. | Whole Team | Medium | High | Unresolved
7 | Medium | poor time-management | The standard and quality of the prototype could be impacted by improper time management for the entire project. | Not finishing task on schedule can lead to more time catching up |  | Finish your work and task on schedule. Stay focus. | Whole Team | High | Medium | Watching
8 | Low-Medium | Workplace injury (Health and Safety) | Not knowning the health and safety hazards of the environment | The project in a factory environment is a first for most of the team |  | Researching and learning the basic health and safety rule of the workshop | Whole Team | Low | High | Watching
9 | High | Legal Issue | The clients need to tell the team their legal or regulation requirements, so that we dont break the client requirements | By not knowing the client's legal or regulation requirements |  | Ask the client if there is any legal or regulation requirements | Team Manager | Low | High | Watching
10 | high | Poor communcation with other members of the team | Not letting your team members know about problems or stuggle that you are having. | Trying to solve issue/problem yourself, or struggling in finishing up your task |  | Letting the team know your issue or problems that you may been having. | Whole Team | Medium | Medium | Watching
11 | high | team member unavailable to participate | Someone might had an issue come up or some sort of personal reason that is preventing them from coming. | Overwhelmed with everday problem/obstacle |  | Letting the team and mentor know about the situation. | Team Members | Medium | Low | Watching
12 | Medium-high | lockdown happening again | Another global pandemic issue according | Not careing about yourself or others during pandemic |  | Staying home when you are not feeling well | Whole Team | Low | High | Watching
13 | high | data loss | data loss includes can be things like PCs we store information break, we lose power | Not setting up or backing up our information as we start making the project |  | having the onedrive and teams to have an online platform as well to keep a constantly updating copy | Whole Team | Medium | Medium | Watching
14 | Medium | requirements beyond scope | client requests deliverables which are way too unrealostic to achieve in time and/or with our skill | The client doesn't know the team's skill range |  | client negotiation, work delegation, or change management plans | Whole Team | high | high | Watching
15 | Medium | Data availability | Docs that we requested from the client in risk register | Might be due to the client policy |  |  | Whole team | Medium | Medium | watching
16 | Medium-high
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: team member unavailable to participate Reply: lockdown happening again Reply: data loss Reply: requirements beyond scope

## Sheet2
# | Risk | Description | Root cause | Potential Responses | Risk Owner | Probability | Threat
1 | Unclear Requirements | Keep open and clear communication with the client's requirements | The project is as new for the client as it is for the team | Keep open and clear communication with the client's requirements | Client Liaison | 40% | medium
[5 empty] | Trigger | Impact | Status
[6 empty] | 60% | Watching
1 | Unclear Requirements | Keep open and clear communication with the client's requirements | The project is as new for the client as it is for the team | Keep open and clear communication with the client's requirements | Client Liaison | 40% | medium
[5 empty] | Trigger | Impact | Status
[6 empty] | 60% | Watching