## Upskilling Schedule
Task Name | Duration | Start | Finish | Predecessors | Assigned To | % Complete | Status | Comments
Plan Upskilling | 1.5d | 2023-04-03 | 2023-04-04 |  | Everyone
Delegate components | 0.5d | 2023-04-03 | 2023-04-03
Research into relevant fields | 1d | 2023-04-03 | 2023-04-04 | 2
Individual Upskilling Period 1 | 4d | 2023-04-04 | 2023-04-08 | 1
Identify key skills/knowledge | 0.5d | 2023-04-04 | 2023-04-04
Upskilling period | 3.5d | 2023-04-05 | 2023-04-08 | 5
Team meeting | 0 | 2023-04-08 | 2023-04-08 | 4 |  |  |  | Updating each other status on how they feel about the upskilling scope and potential risks/mitigation strategies
Upskilling period 2 | 6d | 2023-04-08 | 2023-04-15 | 7
Upskill in fields assigned to all team members | 6d | 2023-04-08 | 2023-04-15
Upskill in delegated fields | 6d | 2023-04-08 | 2023-04-15